## Instructions
RISK ASSESSMENT (RA) TEMPLATE — INSTRUCTIONS
Work at Height ¦ Manual Handling ¦ Hot Job ¦ Crane Activity ¦ and any other task
HOW TO USE THIS TEMPLATE
1. Go to the 'Risk Assessment' tab and list every activity/task in Column C (one row per hazard).
2. Identify the hazard(s) for that activity (Column D) and who/what could be harmed (Column E).
3. Record existing controls already in place (Column F).
4. Score the INITIAL risk: pick Probability 1-3 (Column G) and Consequence (Column H) from the dropdown lists.
The Risk Rating (Column J) calculates automatically and is colour-coded: Low / Medium / High / Extreme.
5. List any ADDITIONAL controls needed to reduce the risk to ALARP (As Low As Reasonably Practicable) in Column K.
6. Re-score the RESIDUAL risk after those additional controls (Columns L & M) - Column O calculates automatically.
7. Assign a Responsible Person and Target Date (Columns P & Q), and track Status in Column R.
8. Review and update this RA whenever the task, equipment or environment changes, or after any incident/near-miss.
COLOUR KEY - RISK RATING
Low | Acceptable - continue with existing controls, monitor periodically.
Medium | Tolerable - implement additional controls before / while proceeding.
High | Unacceptable as-is - STOP and implement additional controls before work starts.
Extreme | STOP WORK - do not proceed. Requires senior management review & elimination/substitution.
PROBABILITY & CONSEQUENCE DEFINITIONS (see 'Risk Matrix' tab for detail)
Probability: 1 = Unlikely 2 = Possible 3 = Likely
Consequence: Minor < Average < Major < High (severity of the worst credible outcome)
Cells shaded yellow in the template are the ones you fill in. All other cells calculate automatically.

## Risk Matrix
RISK MATRIX - REFERENCE (used by formulas in the Risk Assessment tab)
Consequence Severity Lookup |  |  | Probability Scale
Consequence | Severity Value |  | Value | Meaning
Minor | 1 |  | 1 | Unlikely
Average | 2 |  | 2 | Possible
Major | 3 |  | 3 | Likely
High | 4
Risk Score = Probability x Severity -> Rating Band
Score range | Rating
1 - 2 | Low
3 - 4 | Medium
6 - 8 | High
9 - 12 | Extreme
Visual Matrix (Probability rows x Consequence columns)
Probability \ Consequence | Minor | Average | Major | High
1 - Unlikely | Low | Low-Med | Medium | Medium
2 - Possible | Low-Med | Medium | High | High
3 - Likely | Medium | High | High | Extreme

## Risk Assessment
RISK ASSESSMENT TEMPLATE
Yellow-shaded cells = fill in. White cells with grey text = calculate automatically. Freeze panes applied for easy scrolling.
No. | Date | Activity / Task | Hazard Identified | Who / What May Be Harmed | Existing Controls | Prob. (1-3) | Consequence | Risk Score | Initial Risk Rating | Additional Controls Required (ALARP) | Resid. Prob. (1-3) | Resid. Consequence | Resid. Score | Residual Risk Rating | Responsible Person | Target Date | Status
1 | 2026-07-21 | Work at Height - roof edge inspection | Fall from unprotected roof edge | Inspection technician; persons below | Permit to work; harness available | 2 | High | 8 | High | Install edge guardrails; 100% tie-off with double lanyard; exclusion zone below | 1 | High | 4 | Medium | Site Supervisor - A. Khan | 2026-07-25 | In Progress